## Slide 1
BACK Timeline
Part 1: Recruitment and Visit 1
Attend registration and back-to-school events as available
Help nurse collect Asthma Intake Forms
Assess Asthma Intake forms for eligibility
Recruit eligible students into the program
Schedule visit 1 with family
Complete visit 1 with family
  Consent/assent
  Baseline Navigator Questionnaire
  Social Needs Screener
  Social Needs guided conversation with a 2-week check in
  Asthma education
  Family will be sent post-visit survey to complete
Complete visit 1 with student
  IDAT
  Asthma education
For waitlist schools, complete a family visit with Consent/assent, Waitlist Baseline Navigator Questionnaire and Social Needs Screener
July – August
August - December: Visit 1

## Slide 2
BACK Timeline
Part 2: Visit 2 and 3
Schedule visit 2 with family
Family will be sent pre-visit survey to complete
Complete visit 2 with family
  Post baseline demographics survey and pre-visit survey if they did not complete them on their own
  Follow-up Navigator Questionnaire
  SDOH Follow up
  Asthma education
Complete visit 2 with student
  IDAT
  Asthma education
Schedule visit 3 with family
Family will be sent pre-visit survey to complete
Complete visit 3 with family
  Pre-visit survey if they did not complete it on their own
  Follow-up Navigator Questionnaire
  SDOH Follow up
  Asthma education
Complete visit 3 with student
  IDAT
  Asthma education
January - March: Visit 2
March - May: Visit 3

## Slide 3
BACK Timeline
Part 3: End of the school year and summer
Family will be sent annual survey to complete
ANs will be sent annual survey to complete
Confirm school nurse participation in BACK next year
Find out about any planned registrations or back to school events for next school year
Find out about any planned registrations or back to school events for next school year
Complete further training and professional development
Prepare for upcoming school year
May – June
June – July